## Defect Log
Sl No | Detected Sprint | Assigned To | Type of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | Sprint 1 | Developer | Functional | Designed overall system architecture and multi-agent workflow | 11-07-2026 | Closed | Verified
2 | Sprint 1 | Developer | Functional | Implemented Code Submission Module for Python and Java | 12-07-2026 | Closed | Verified
3 | Sprint 1 | Developer | Functional | Added source code paste functionality | 12-07-2026 | Closed | Verified
4 | Sprint 1 | Developer | Functional | Added Python and Java file upload support | 12-07-2026 | Closed | Verified
5 | Sprint 1 | Developer | Validation | Implemented automatic language detection | 13-07-2026 | Closed | Verified
6 | Sprint 1 | Developer | Validation | Added Python syntax validation using AST | 13-07-2026 | Closed | Verified
7 | Sprint 1 | Developer | Validation | Added Java syntax validation using javalang | 14-07-2026 | Closed | Verified
8 | Sprint 1 | Developer | Validation | Built Secure Coding Knowledge Base | 15-07-2026 | Closed | Verified
9 | Sprint 1 | Developer | Functional | Indexed OWASP documentation into ChromaDB | 16-07-2026 | Closed | Verified
10 | Sprint 1 | Developer | Functional | Implemented document chunking pipeline | 16-07-2026 | Closed | Verified
11 | Sprint 1 | Developer | Functional | Added embedding generation using HuggingFace | 17-07-2026 | Closed | Verified
12 | Sprint 1 | Developer | Functional | Configured Chroma Vector Database | 18-07-2026 | Closed | Verified
13 | Sprint 1 | Developer | Functional | Connected Groq LLM with RAG pipeline | 19-07-2026 | Closed | Verified
14 | Sprint 1 | Developer | UI | Designed initial Streamlit interface | 20-07-2026 | Closed | Verified
15 | Sprint 1 | Developer | Integration | Verified end to end Code Submission and RAG initialization | 23-07-2026 | Closed | Milestone Completed
16 | Sprint 2 | Developer | Functional | Added SQL Injection detection logic | 17-07-2026 | Closed | Verified
17 | Sprint 2 | Developer | Functional | Improved SQL Injection regex patterns | 17-07-2026 | Closed | Fixed
18 | Sprint 2 | Developer | Functional | Added Hardcoded Secret detection | 17-07-2026 | Closed | Verified
19 | Sprint 2 | Developer | Functional | Added Weak Password detection | 17-07-2026 | Closed | Verified
20 | Sprint 2 | Developer | Functional | Added eval() usage detection | 17-07-2026 | Closed | Verified
21 | Sprint 2 | Developer | Functional | Added Command Injection detection | 18-07-2026 | Closed | Verified
22 | Sprint 2 | Developer | Functional | Added Weak Cryptography detection | 18-07-2026 | Closed | Verified
23 | Sprint 2 | Developer | Functional | Added Cross Site Scripting (XSS) detection | 18-07-2026 | Closed | Verified
24 | Sprint 2 | Developer | Functional | Added Path Traversal detection | 19-07-2026 | Closed | Verified
25 | Sprint 2 | Developer | Functional | Added Insecure Deserialization detection | 19-07-2026 | Closed | Verified
26 | Sprint 2 | Developer | Functional | Added Weak Random Number detection | 19-07-2026 | Closed | Verified
27 | Sprint 2 | Developer | Functional | Added CSRF detection | 20-07-2026 | Closed | Verified
28 | Sprint 2 | Developer | Functional | Added SSRF detection | 20-07-2026 | Closed | Verified
29 | Sprint 2 | Developer | Functional | Added XXE detection | 20-07-2026 | Closed | Verified
30 | Sprint 2 | Developer | Functional | Added Weak JWT detection | 20-07-2026 | Closed | Verified
31 | Sprint 2 | Developer | Functional | Added Debug Mode detection | 20-07-2026 | Closed | Verified
32 | Sprint 2 | Developer | Functional | Added Console Output detection | 20-07-2026 | Closed | Verified
33 | Sprint 2 | Developer | Functional | Added Long Line detection | 20-07-2026 | Closed | Verified
34 | Sprint 2 | Developer | Functional | Added Long Method detection | 20-07-2026 | Closed | Verified
35 | Sprint 2 | Developer | Functional | Added Too Many Parameters detection | 20-07-2026 | Closed | Verified
36 | Sprint 2 | Developer | Functional | Added Magic Number detection | 20-07-2026 | Closed | Verified
37 | Sprint 2 | Developer | Functional | Added TODO/FIXME Comment detection | 20-07-2026 | Closed | Verified
38 | Sprint 2 | Developer | Functional | Added Duplicate Import detection | 20-07-2026 | Closed | Verified
39 | Sprint 2 | Developer | Functional | Added Unused Import detection | 20-07-2026 | Closed | Verified
40 | Sprint 2 | Developer | Functional | Added Global Variable detection | 20-07-2026 | Closed | Verified
41 | Sprint 2 | Developer | Functional | Added Bare Exception detection | 20-07-2026 | Closed | Verified
42 | Sprint 2 | Developer | Functional | Added Empty Exception Block detection | 20-07-2026 | Closed | Verified
43 | Sprint 2 | Developer | Functional | Added Generic Exception detection | 20-07-2026 | Closed | Verified
44 | Sprint 2 | Developer | Functional | Added Infinite Loop detection | 20-07-2026 | Closed | Verified
45 | Sprint 2 | Developer | Functional | Added Deep Nesting detection | 20-07-2026 | Closed | Verified
46 | Sprint 2 | Developer | Validation | Improved Java syntax validation | 20-07-2026 | Closed | Verified
47 | Sprint 2 | Developer | Performance | Optimized modular detection pipeline | 20-07-2026 | Closed | Improved Performance
48 | Sprint 2 | Developer | UI | Improved consolidated findings display | 20-07-2026 | Closed | Verified
49 | Sprint 2 | Developer | Integration | Integrated Code Analysis and Security Agents | 23-07-2026 | Closed | Milestone Completed
50 | Sprint 3 | Developer | Functional | Developed Remediation Agent | 24-07-2026 | Closed | Verified
51 | Sprint 3 | Developer | Functional | Added corrected secure code generation | 24-07-2026 | Closed | Verified
52 | Sprint 3 | Developer | Functional | Added secure coding best practice explanations | 24-07-2026 | Closed | Verified
53 | Sprint 3 | Developer | Functional | Developed PR Summary Agent | 25-07-2026 | Closed | Verified
54 | Sprint 3 | Developer | Functional | Generated executive review summary | 25-07-2026 | Closed | Verified
55 | Sprint 3 | Developer | Functional | Added prioritized remediation roadmap | 25-07-2026 | Closed | Verified
56 | Sprint 3 | Developer | UI | Developed Findings Display dashboard | 26-07-2026 | Closed | Verified
57 | Sprint 3 | Developer | UI | Added severity cards and issue statistics | 26-07-2026 | Closed | Verified
58 | Sprint 3 | Developer | UI | Implemented detailed findings table | 26-07-2026 | Closed | Verified
59 | Sprint 3 | Developer | UI | Added Code Health Score visualization | 26-07-2026 | Closed | Verified
60 | Sprint 3 | Developer | Integration | Unified outputs from all AI agents | 27-07-2026 | Closed | Verified
61 | Sprint 3 | Developer | Functional | Developed Conversational Code Assistant | 28-07-2026 | Closed | Verified
62 | Sprint 3 | Developer | Functional | Connected Assistant with ChromaDB | 28-07-2026 | Closed | Verified
63 | Sprint 3 | Developer | Functional | Integrated Groq LLM with RAG retrieval | 29-07-2026 | Closed | Verified
64 | Sprint 3 | Developer | Functional | Added conversation history | 29-07-2026 | Closed | Verified
65 | Sprint 3 | Developer | Functional | Generated PDF Code Review Report | 30-07-2026 | Closed | Verified
66 | Sprint 3 | Developer | Functional | Added report export functionality | 30-07-2026 | Closed | Verified
67 | Sprint 3 | Developer | UI | Redesigned Streamlit application interface | 31-07-2026 | Closed | Verified
68 | Sprint 3 | Developer | UI | Developed Analytics Dashboard | 31-07-2026 | Closed | Verified
69 | Sprint 3 | Developer | UI | Implemented History page | 31-07-2026 | Closed | Verified
70 | Sprint 3 | Developer | UI | Added Settings page | 31-07-2026 | Closed | Verified
71 | Sprint 3 | Developer | Integration | Integrated all AI agents with dashboard | 01-08-2026 | Closed | Verified
72 | Sprint 3 | Developer | Integration | Connected RAG Assistant with Knowledge Base | 02-08-2026 | Closed | Verified
73 | Sprint 3 | Developer | Functional | Resolved module import and initialization issues | 03-08-2026 | Closed | Verified
74 | Sprint 3 | Developer | Validation | Conducted end-to-end testing using Java programs | 04-08-2026 | Closed | Verified
75 | Sprint 3 | Developer | Validation | Conducted end-to-end testing using Python programs | 04-08-2026 | Closed | Verified
76 | Sprint 3 | Developer | Validation | Verified dashboard, reports and AI Assistant workflow | 04-08-2026 | Closed | Verified
77 | Sprint 3 | Developer | Performance | Optimized lazy loading of AI models and RAG components | 05-08-2026 | Closed | Improved Performance
78 | Sprint 3 | Developer | Integration | Completed final system integration and validation | 05-08-2026 | Closed | Final Milestone Completed
79 | Sprint 4 | Developer | Functional | Enhanced PDF Code Review Report with executive summary, severity breakdown, remediation roadmap and overall code quality assessment | 08-08-2026 | Closed | Verified
80 | Sprint 4 | Developer | Validation | Tested PDF report generation using vulnerable Python code samples | 08-08-2026 | Closed | Verified
81 | Sprint 4 | Developer | Validation | Tested PDF report generation using vulnerable Java code samples | 09-08-2026 | Closed | Verified
82 | Sprint 4 | Developer | Validation | Performed end-to-end testing of complete multi-agent pipeline | 09-08-2026 | Closed | Verified
83 | Sprint 4 | Developer | Validation | Verified Code Analysis Agent accuracy using multiple Python test cases | 10-08-2026 | Closed | Verified
84 | Sprint 4 | Developer | Validation | Verified Security Vulnerability Agent detection accuracy against OWASP vulnerabilities | 10-08-2026 | Closed | Verified
85 | Sprint 4 | Developer | Validation | Validated Remediation Agent recommendations and corrected code generation | 11-08-2026 | Closed | Verified
86 | Sprint 4 | Developer | Validation | Evaluated PR Summary Agent output for completeness and readability | 11-08-2026 | Closed | Verified
87 | Sprint 4 | Developer | Validation | Validated Conversational Code Assistant responses using secure coding knowledge base | 12-08-2026 | Closed | Verified
88 | Sprint 4 | Developer | Performance | Optimized LangGraph multi-agent orchestration workflow | 12-08-2026 | Closed | Improved Performance
89 | Sprint 4 | Developer | Performance | Optimized RAG retrieval quality and document relevance | 13-08-2026 | Closed | Improved Retrieval
90 | Sprint 4 | Developer | Performance | Improved severity scoring consistency across Code Analysis and Security Agents | 13-08-2026 | Closed | Verified
91 | Sprint 4 | Developer | UI | Refined Streamlit dashboard, findings presentation and report interface | 14-08-2026 | Closed | Verified
92 | Sprint 4 | Developer | Documentation | Prepared technical documentation, architecture diagrams and implementation details | 14-08-2026 | Closed | Verified
93 | Sprint 4 | Developer | Validation | Demonstrated analysis on three Python and Java code samples with varying complexity | 15-08-2026 | Closed | Verified
94 | Sprint 4 | Developer | Integration | Completed final system testing, documentation review and project demonstration | 16-08-2026 | Closed | Final Milestone Completed