## Defect Tracker
Sl No | Detected Sprint | Assigned To | Type of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | Sprint 2 | Developer | Functional | Added _detect_sql_injection() detection logic | 17-07-2026 | Closed | Verified
2 | Sprint 2 | Developer | Functional | Improved SQL Injection regex patterns | 17-07-2026 | Closed | Fixed
3 | Sprint 2 | Developer | Functional | Added _detect_hardcoded_secret() detection | 17-07-2026 | Closed | Verified
4 | Sprint 2 | Developer | Functional | Added _detect_weak_password() detection | 17-07-2026 | Closed | Verified
5 | Sprint 2 | Developer | Functional | Added _detect_eval_usage() detection | 17-07-2026 | Closed | Verified
6 | Sprint 2 | Developer | Functional | Added _detect_command_injection() detection | 18-07-2026 | Closed | Verified
7 | Sprint 2 | Developer | Functional | Added _detect_weak_crypto() detection | 18-07-2026 | Closed | Verified
8 | Sprint 2 | Developer | Functional | Added _detect_xss() detection | 18-07-2026 | Closed | Verified
9 | Sprint 2 | Developer | Functional | Added _detect_path_traversal() detection | 19-07-2026 | Closed | Verified
10 | Sprint 2 | Developer | Functional | Added _detect_insecure_deserialization() detection | 19-07-2026 | Closed | Verified
11 | Sprint 2 | Developer | Functional | Added _detect_weak_random() detection | 19-07-2026 | Closed | Verified
12 | Sprint 2 | Developer | Functional | Added _detect_csrf() detection | 20-07-2026 | Closed | Verified
13 | Sprint 2 | Developer | Functional | Added _detect_ssrf() detection | 20-07-2026 | Closed | Verified
14 | Sprint 2 | Developer | Functional | Added _detect_xxe() detection | 20-07-2026 | Closed | Verified
15 | Sprint 2 | Developer | Functional | Added _detect_weak_jwt() detection | 20-07-2026 | Closed | Verified
16 | Sprint 2 | Developer | Functional | Added _detect_debug_mode() detection | 20-07-2026 | Closed | Verified
17 | Sprint 2 | Developer | Functional | Implemented Console Output detection | 20-07-2026 | Closed | Verified
18 | Sprint 2 | Developer | Functional | Implemented Long Line detection | 20-07-2026 | Closed | Verified
19 | Sprint 2 | Developer | Functional | Implemented Long Method detection | 20-07-2026 | Closed | Verified
20 | Sprint 2 | Developer | Functional | Implemented Too Many Parameters detection | 20-07-2026 | Closed | Verified
21 | Sprint 2 | Developer | Functional | Implemented Magic Number detection | 20-07-2026 | Closed | Verified
22 | Sprint 2 | Developer | Functional | Implemented TODO/FIXME Comment detection | 20-07-2026 | Closed | Verified
23 | Sprint 2 | Developer | Functional | Implemented Duplicate Import detection | 20-07-2026 | Closed | Verified
24 | Sprint 2 | Developer | Functional | Implemented Unused Import detection | 20-07-2026 | Closed | Verified
25 | Sprint 2 | Developer | Functional | Implemented Global Variable detection | 20-07-2026 | Closed | Verified
26 | Sprint 2 | Developer | Functional | Implemented Bare Except detection | 20-07-2026 | Closed | Verified
27 | Sprint 2 | Developer | Functional | Implemented Empty Exception Block detection | 20-07-2026 | Closed | Verified
28 | Sprint 2 | Developer | Functional | Implemented Generic Exception Catch detection | 20-07-2026 | Closed | Verified
29 | Sprint 2 | Developer | Functional | Implemented Possible Infinite Loop detection | 20-07-2026 | Closed | Verified
30 | Sprint 2 | Developer | Functional | Implemented Deep Nesting detection | 20-07-2026 | Closed | Verified
31 | Sprint 2 | Developer | Validation | Improved Java syntax validation using fallback wrapper | 20-07-2026 | Closed | Expected Behavior
32 | Sprint 2 | Developer | Performance | Optimized source code scanning using modular detection methods | 20-07-2026 | Closed | Improved Performance
33 | Sprint 2 | Developer | UI | Improved consolidated findings display with severity classification | 20-07-2026 | Closed | Verified