## Sprint Retrospective
SL # | Sprint # | Sprint Start Date | Sprint End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 04-Jul-2026 | 12-Jul-2026 | Rajashekar Kanneboina | Add automated unit testing for code validation modules. | Manual language selection during testing. | Improving Streamlit UI and usability. | Implemented automatic language detection and completed UI fixes.
2 | Sprint 1 | 04-Jul-2026 | 12-Jul-2026 | Rajashekar Kanneboina | Increase Java syntax validation accuracy. | Ignoring parser exceptions. | Regular testing after every feature. | Added exception handling and fallback validation.
3 | Sprint 1 | 04-Jul-2026 | 12-Jul-2026 | Rajashekar Kanneboina | Improve dashboard responsiveness. | Delaying UI testing until the end. | Collecting feedback after each module. | Redesigned dashboard layout using Streamlit columns and containers.
4 | Sprint 2 | 15-Jul-2026 | 22-Jul-2026 | Rajashekar Kanneboina | Improve SQL Injection detection accuracy. | Using overly broad regex patterns. | Updating the secure coding knowledge base. | Refined SQL detection logic and reduced false positives.
5 | Sprint 2 | 15-Jul-2026 | 22-Jul-2026 | Rajashekar Kanneboina | Standardize report generation modules. | Keeping inconsistent finding keys. | Testing report generation after every update. | Fixed KeyError and standardized report fields.
6 | Sprint 2 | 15-Jul-2026 | 22-Jul-2026 | Rajashekar Kanneboina | Expand Java language detection patterns. | Relying only on file extensions. | Functional testing of detection modules. | Enhanced Java keyword detection for pasted code.
7 | Sprint 2 | 15-Jul-2026 | 22-Jul-2026 | Rajashekar Kanneboina | Perform complete integration testing before release. | Skipping final verification. | Maintaining project documentation and knowledge base. | Executed all test cases, rebuilt the knowledge base, and resolved remaining issues.