## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 8.5 | 1.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Create Streamlit Project | 03-Jul-2026 | 03-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-002 | Implement File Upload Module | 03-Jul-2026 | 03-Jul-2026 | Rajashekar | Development | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-003 | Implement Code Paste Module | 04-Jul-2026 | 04-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-004 | Language Detection Module | 05-Jul-2026 | 05-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-005 | Python Syntax Validation | 06-Jul-2026 | 06-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-006 | Java Syntax Validation | 07-Jul-2026 | 07-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-007 | Dashboard UI | 08-Jul-2026 | 08-Jul-2026 | Rajashekar | UI Development | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-008 | Submission Details UI | 09-Jul-2026 | 09-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-009 | Integrate Modules | 10-Jul-2026 | 10-Jul-2026 | Rajashekar | Integration | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-010 | Sprint 1 Testing | 11-Jul-2026 | 12-Jul-2026 | Rajashekar | Testing | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-006 | T-011 | Implement SQL Injection Detection | 14-Jul-2026 | 14-Jul-2026 | Rajashekar | Development | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T-012 | Implement Hardcoded Secret Detection | 14-Jul-2026 | 14-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T-013 | Implement Weak Password Detection | 15-Jul-2026 | 15-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T-014 | Implement Command Injection Detection | 15-Jul-2026 | 16-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T-015 | Implement Path Traversal Detection | 16-Jul-2026 | 16-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T-016 | Implement XSS Detection | 17-Jul-2026 | 17-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T-017 | Implement Weak Cryptography Detection | 18-Jul-2026 | 18-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T-018 | Implement Insecure Deserialization Detection | 18-Jul-2026 | 19-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T-019 | Implement Weak Random Detection | 19-Jul-2026 | 19-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T-020 | Generate Consolidated PDF Report | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T-021 | Build OWASP RAG Knowledge Base | 20-Jul-2026 | 21-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | T-022 | Implement Analysis History | 21-Jul-2026 | 21-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | T-023 | Implement Settings Module | 22-Jul-2026 | 22-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
US-015 | T-024 | Sprint 2 Integration Testing & Bug Fixes | 22-Jul-2026 | 22-Jul-2026 | Rajashekar | Testing | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0