## Sheet1
Sprint | Day | Impediments | Action Taken
Sprint 1 | 04-Jul-2026 | Java file upload not working correctly | Updated file uploader to support both `.py` and `.java` files.
Sprint 1 | 06-Jul-2026 | Auto language detection failed for pasted Java code | Improved regex patterns and Java keyword detection.
Sprint 1 | 08-Jul-2026 | Java syntax validator produced parsing errors | Added fallback validation and improved exception handling.
Sprint 1 | 10-Jul-2026 | Dashboard layout alignment issues | Redesigned the Streamlit UI using columns and containers.
Sprint 1 | 12-Jul-2026 | Minor UI bugs found during testing | Fixed UI and completed Sprint 1 testing.
Sprint 2 | 15-Jul-2026 | SQL Injection detection generated false positives | Refined SQL detection logic and regex patterns.
Sprint 2 | 17-Jul-2026 | PDF report generation failed (`KeyError: 'issue'`) | Standardized finding keys and updated the report generator.
Sprint 2 | 19-Jul-2026 | Java code pasted in editor detected as Unknown | Enhanced language detection with additional Java patterns.
Sprint 2 | 21-Jul-2026 | Knowledge Base build failed due to missing files | Corrected document paths and rebuilt the knowledge base.
Sprint 2 | 22-Jul-2026 | Final security findings required verification | Executed all test cases and fixed remaining issues.