## User Stories
Sl No | Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | Sprint 1 | Sprint 1 | US-001 | As a user, I want to upload Python and Java source files for code review. | Must | None | Rajashekar Kanneboina | Completed
2 | Sprint 1 | Sprint 1 | US-002 | As a user, I want to paste Python or Java source code directly into the application. | Must | None | Rajashekar Kanneboina | Completed
3 | Sprint 1 | Sprint 1 | US-003 | As a user, I want automatic programming language detection. | Must | Code Submission Module | Rajashekar Kanneboina | Completed
4 | Sprint 1 | Sprint 1 | US-004 | As a user, I want syntax validation before AI analysis starts. | Must | Language Detection | Rajashekar Kanneboina | Completed
5 | Sprint 1 | Sprint 1 | US-005 | As a user, I want an OWASP secure coding knowledge base built using RAG. | Must | Knowledge Base | Rajashekar Kanneboina | Completed
6 | Sprint 1 | Sprint 1 | US-006 | As a user, I want an intuitive Streamlit dashboard for code submission. | Should | Syntax Validation | Rajashekar Kanneboina | Completed
7 | Sprint 2 | Sprint 2 | US-007 | As a user, I want Code Analysis Agent to review code quality and best practices. | Must | Submission Module | Rajashekar Kanneboina | Completed
8 | Sprint 2 | Sprint 2 | US-008 | As a user, I want Security Vulnerability Agent to detect SQL Injection vulnerabilities. | Must | Security Agent | Rajashekar Kanneboina | Completed
9 | Sprint 2 | Sprint 2 | US-009 | As a user, I want Security Vulnerability Agent to detect Hardcoded Secrets. | Must | Security Agent | Rajashekar Kanneboina | Completed
10 | Sprint 2 | Sprint 2 | US-010 | As a user, I want detection of Weak Authentication and Weak Password issues. | Must | Security Agent | Rajashekar Kanneboina | Completed
11 | Sprint 2 | Sprint 2 | US-011 | As a user, I want OWASP vulnerability detection for XSS, Command Injection, Path Traversal, SSRF, XXE and related issues. | Must | Security Agent | Rajashekar Kanneboina | Completed
12 | Sprint 2 | Sprint 2 | US-012 | As a user, I want code quality analysis using PMD, Checkstyle, Pylint and Radon. | Should | Code Analysis Agent | Rajashekar Kanneboina | Completed
13 | Sprint 2 | Sprint 2 | US-013 | As a user, I want Code Analysis and Security Agents to execute automatically in a multi-agent workflow. | Must | LangGraph Workflow | Rajashekar Kanneboina | Completed
14 | Sprint 2 | Sprint 2 | US-014 | As a user, I want severity classification for every detected issue. | Must | Multi-Agent Pipeline | Rajashekar Kanneboina | Completed
15 | Sprint 2 | Sprint 2 | US-015 | As a user, I want a consolidated findings dashboard with overall Code Health Score. | Should | Findings Module | Rajashekar Kanneboina | Completed
16 | Sprint 3 | Sprint 3 | US-016 | As a user, I want Remediation Agent to generate secure fix recommendations. | Must | Security Findings | Rajashekar Kanneboina | Completed
17 | Sprint 3 | Sprint 3 | US-017 | As a user, I want corrected secure code examples for every detected issue. | Must | Remediation Agent | Rajashekar Kanneboina | Completed
18 | Sprint 3 | Sprint 3 | US-018 | As a user, I want PR Summary Agent to generate executive review summaries. | Must | All Agents | Rajashekar Kanneboina | Completed
19 | Sprint 3 | Sprint 3 | US-019 | As a user, I want AI-generated severity breakdown and prioritized remediation roadmap. | Should | PR Summary Agent | Rajashekar Kanneboina | Completed
20 | Sprint 3 | Sprint 3 | US-020 | As a user, I want a RAG-powered Conversational Code Assistant for secure coding guidance. | Must | Knowledge Base | Rajashekar Kanneboina | Completed
21 | Sprint 3 | Sprint 3 | US-021 | As a user, I want conversation history maintained during AI Assistant interactions. | Should | Conversational Assistant | Rajashekar Kanneboina | Completed
22 | Sprint 3 | Sprint 3 | US-022 | As a user, I want exportable PDF Code Review Reports containing findings, remediation and summaries. | Must | Report Module | Rajashekar Kanneboina | Completed
23 | Sprint 3 | Sprint 3 | US-023 | As a user, I want Analytics Dashboard showing severity metrics and review statistics. | Should | Dashboard Module | Rajashekar Kanneboina | Completed
24 | Sprint 3 | Sprint 3 | US-024 | As a user, I want lazy loading of AI and RAG components for faster startup performance. | Could | AI Assistant | Rajashekar Kanneboina | Completed
25 | Sprint 3 | Sprint 3 | US-025 | As a user, I want end-to-end integration of all AI agents into a single review pipeline. | Must | All Modules | Rajashekar Kanneboina | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75.5 | 6.5 | 6.5 | 5 | 4.5 | 4 | 6.5 | 14.25 | 7.25 | 7.5 | 5 | 1.5 | 3.5 | 3.5 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Create Streamlit Project Structure | 03-Jul-2026 | 03-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-002 | Design Multi-page Navigation Layout | 03-Jul-2026 | 03-Jul-2026 | Rajashekar | UI Development | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-003 | Implement Source Code Paste Module | 04-Jul-2026 | 04-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-004 | Implement File Upload Module | 04-Jul-2026 | 04-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T-005 | Automatic Language Detection Module | 05-Jul-2026 | 05-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-006 | Python Syntax Validation | 06-Jul-2026 | 06-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T-007 | Java Syntax Validation | 07-Jul-2026 | 07-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-008 | Submission Information Dashboard | 08-Jul-2026 | 08-Jul-2026 | Rajashekar | UI Development | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T-009 | Integrate Submission Workflow | 09-Jul-2026 | 09-Jul-2026 | Rajashekar | Integration | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-010 | Create Secure Coding Knowledge Base | 09-Jul-2026 | 10-Jul-2026 | Rajashekar | Development | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-011 | Load OWASP Documents | 10-Jul-2026 | 10-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-012 | Document Chunking Module | 10-Jul-2026 | 10-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T-013 | Embedding Generation Module | 11-Jul-2026 | 11-Jul-2026 | Rajashekar | Development | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
US-006 | T-014 | ChromaDB Vector Store Creation | 11-Jul-2026 | 11-Jul-2026 | Rajashekar | Development | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0
US-007 | T-015 | Sprint 1 Integration Testing | 12-Jul-2026 | 12-Jul-2026 | Rajashekar | Testing | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-008 | T-016 | SQL Injection Detection | 14-Jul-2026 | 14-Jul-2026 | Rajashekar | Development | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T-017 | Hardcoded Secret Detection | 14-Jul-2026 | 14-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T-018 | Weak Password Detection | 15-Jul-2026 | 15-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T-019 | Command Injection Detection | 15-Jul-2026 | 16-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T-020 | Path Traversal Detection | 16-Jul-2026 | 16-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T-021 | Cross-Site Scripting (XSS) Detection | 17-Jul-2026 | 17-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T-022 | Weak Cryptography Detection | 18-Jul-2026 | 18-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T-023 | Insecure Deserialization Detection | 18-Jul-2026 | 19-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T-024 | Weak Random Detection | 19-Jul-2026 | 19-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T-025 | CSRF Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T-026 | SSRF Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T-027 | XXE Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T-028 | Weak JWT Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T-029 | Debug Mode Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T-030 | Console Output Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T-031 | Long Line Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T-032 | Long Method Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | T-033 | Too Many Parameters Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T-034 | Magic Number Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T-035 | TODO/FIXME Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T-036 | Duplicate Import Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T-037 | Unused Import Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T-038 | Global Variable Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T-039 | Bare Except Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T-040 | Empty Exception Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | T-041 | Generic Exception Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T-042 | Infinite Loop Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T-043 | Deep Nesting Detection | 20-Jul-2026 | 20-Jul-2026 | Rajashekar | Development | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | T-044 | Multi-Agent Orchestration | 21-Jul-2026 | 22-Jul-2026 | Rajashekar | Integration | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-017 | T-045 | Severity Scoring Engine | 22-Jul-2026 | 22-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
US-018 | T-046 | Sprint 2 Testing & Bug Fixes | 23-Jul-2026 | 23-Jul-2026 | Rajashekar | Testing | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-019 | T-047 | Develop Remediation Agent | 24-Jul-2026 | 24-Jul-2026 | Rajashekar | Development | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | T-048 | Generate Corrected Code Examples | 24-Jul-2026 | 24-Jul-2026 | Rajashekar | Development | Completed | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | T-049 | Build PR Summary Agent | 25-Jul-2026 | 25-Jul-2026 | Rajashekar | Development | Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | T-050 | Generate Executive Summary | 25-Jul-2026 | 25-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-020 | T-051 | Generate Severity Breakdown | 25-Jul-2026 | 25-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-021 | T-052 | Findings Dashboard UI | 26-Jul-2026 | 26-Jul-2026 | Rajashekar | UI Development | Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-021 | T-053 | Code Health Score Dashboard | 26-Jul-2026 | 26-Jul-2026 | Rajashekar | UI Development | Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-021 | T-054 | Detailed Findings Table | 27-Jul-2026 | 27-Jul-2026 | Rajashekar | UI Development | Completed | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-022 | T-055 | Unified Findings Integration | 27-Jul-2026 | 27-Jul-2026 | Rajashekar | Integration | Completed | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-023 | T-056 | Build Conversational Code Assistant | 28-Jul-2026 | 28-Jul-2026 | Rajashekar | Development | Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-023 | T-057 | Integrate RAG Retrieval Pipeline | 29-Jul-2026 | 29-Jul-2026 | Rajashekar | Development | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-023 | T-058 | Integrate Groq LLM | 29-Jul-2026 | 29-Jul-2026 | Rajashekar | Development | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-023 | T-059 | Conversation History Support | 29-Jul-2026 | 29-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-024 | T-060 | PDF Report Generation | 30-Jul-2026 | 30-Jul-2026 | Rajashekar | Development | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-024 | T-061 | Export Findings & PR Summary | 30-Jul-2026 | 30-Jul-2026 | Rajashekar | Development | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-025 | T-062 | Streamlit UI Redesign | 31-Jul-2026 | 31-Jul-2026 | Rajashekar | UI Development | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-025 | T-063 | Analytics Dashboard | 31-Jul-2026 | 31-Jul-2026 | Rajashekar | UI Development | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
US-026 | T-064 | Integrate All AI Agents | 01-Aug-2026 | 01-Aug-2026 | Rajashekar | Integration | Completed | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
US-026 | T-065 | Integrate AI Assistant with Knowledge Base | 02-Aug-2026 | 02-Aug-2026 | Rajashekar | Integration | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0
US-027 | T-066 | Fix Module Import & Agent Initialization Issues | 03-Aug-2026 | 03-Aug-2026 | Rajashekar | Development | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0
US-028 | T-067 | End-to-End Testing (Python & Java) | 04-Aug-2026 | 04-Aug-2026 | Rajashekar | Testing | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
US-028 | T-068 | Validate Reports, Dashboard & AI Assistant | 04-Aug-2026 | 04-Aug-2026 | Rajashekar | Validation | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0
US-029 | T-069 | Optimize Lazy Loading of AI Components | 05-Aug-2026 | 05-Aug-2026 | Rajashekar | Performance | Completed | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0
US-029 | T-070 | Final System Integration & Validation | 05-Aug-2026 | 05-Aug-2026 | Rajashekar | Integration | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 04-Jul-2026 | Java file upload not working correctly | Updated file uploader to support both .py and .java files.
Sprint 1 | 06-Jul-2026 | Auto language detection failed for pasted Java code | Improved regex patterns and Java keyword detection.
Sprint 1 | 08-Jul-2026 | Java syntax validator produced parsing errors | Added fallback validation and improved exception handling.
Sprint 1 | 10-Jul-2026 | Dashboard layout alignment issues | Redesigned the Streamlit UI using columns and containers.
Sprint 1 | 11-Jul-2026 | OWASP documents were not loading into Knowledge Base | Corrected document loader and validated document paths.
Sprint 1 | 12-Jul-2026 | Vector database initialization failed during indexing | Rebuilt ChromaDB index and verified embedding generation.
Sprint 1 | 12-Jul-2026 | Minor UI bugs found during testing | Fixed UI issues and completed Sprint 1 testing successfully.
Sprint 2 | 14-Jul-2026 | SQL Injection detection generated false positives | Refined SQL detection logic and improved regex patterns.
Sprint 2 | 15-Jul-2026 | Hardcoded secret detection missed some API key formats | Expanded secret detection patterns and validated multiple key formats.
Sprint 2 | 16-Jul-2026 | Weak password detection produced inconsistent results | Standardized password validation rules and updated detection logic.
Sprint 2 | 17-Jul-2026 | PDF report generation failed (KeyError: 'issue') | Standardized finding keys and updated report generator.
Sprint 2 | 18-Jul-2026 | Java code pasted in editor detected as Unknown | Enhanced language detection using additional Java syntax patterns.
Sprint 2 | 19-Jul-2026 | SpotBugs skipped analysis because .class files were unavailable | Added graceful handling when compiled Java classes are not provided.
Sprint 2 | 20-Jul-2026 | Duplicate findings from multiple analysis tools | Implemented findings normalization and duplicate filtering.
Sprint 2 | 21-Jul-2026 | Knowledge Base build failed due to missing documents | Corrected document paths and rebuilt the ChromaDB knowledge base.
Sprint 2 | 22-Jul-2026 | Security findings required verification before integration | Executed Python and Java validation test cases and fixed remaining issues.
Sprint 2 | 23-Jul-2026 | Multi-agent outputs were not merged correctly | Implemented unified findings aggregation with severity normalization.
Sprint 3 | 24-Jul-2026 | Remediation Agent generated inconsistent recommendations | Standardized remediation templates and improved LLM prompting.
Sprint 3 | 25-Jul-2026 | PR Summary Agent missed severity statistics | Added severity aggregation and executive summary generation.
Sprint 3 | 26-Jul-2026 | Code Health Score calculation produced incorrect values | Revised health score algorithm based on severity weights.
Sprint 3 | 27-Jul-2026 | Findings dashboard did not refresh after new analysis | Added Streamlit session state updates and automatic refresh.
Sprint 3 | 28-Jul-2026 | Conversational Assistant failed when Knowledge Base was unavailable | Added fallback exception handling and user-friendly error messages.
Sprint 3 | 29-Jul-2026 | RAG pipeline initialization increased application startup time | Implemented lazy loading of embeddings and vector store.
Sprint 3 | 30-Jul-2026 | PDF report formatting issues for long findings | Improved report layout, pagination, and text wrapping.
Sprint 3 | 31-Jul-2026 | Analytics dashboard charts displayed inconsistent metrics | Corrected aggregation logic and synchronized dashboard calculations.
Sprint 3 | 01-Aug-2026 | Agent orchestration produced duplicate recommendations | Refined orchestration workflow and merged duplicate findings.
Sprint 3 | 02-Aug-2026 | Conversation history was not retained between queries | Implemented st.session_state based chat history management.
Sprint 3 | 03-Aug-2026 | Module import errors after project restructuring | Updated import paths and resolved package dependency issues.
Sprint 3 | 04-Aug-2026 | End-to-end testing revealed report generation inconsistencies | Validated all modules using Python and Java test cases and fixed issues.
Sprint 3 | 05-Aug-2026 | Final integration and performance optimization required | Optimized AI component loading, completed full system validation, and finalized release.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 03-Jul-2026 | 12-Jul-2026 | Rajashekar Kanneboina | Add automated unit testing for syntax validation modules. | Manual language selection during testing. | Improving Streamlit UI and usability. | Implemented automatic language detection and completed UI improvements.
2 | Sprint 1 | 03-Jul-2026 | 12-Jul-2026 | Rajashekar Kanneboina | Increase Java syntax validation accuracy. | Ignoring parser exceptions. | Regular testing after every feature. | Added fallback validation and improved exception handling.
3 | Sprint 1 | 03-Jul-2026 | 12-Jul-2026 | Rajashekar Kanneboina | Improve Knowledge Base indexing process. | Manual document loading. | Building secure coding knowledge base. | Implemented automated document chunking, embeddings, and ChromaDB indexing.
4 | Sprint 1 | 03-Jul-2026 | 12-Jul-2026 | Rajashekar Kanneboina | Improve dashboard responsiveness. | Delaying UI testing until project completion. | Collecting feedback after each completed module. | Redesigned Streamlit dashboard using columns and containers.
5 | Sprint 2 | 14-Jul-2026 | 23-Jul-2026 | Rajashekar Kanneboina | Improve SQL Injection detection accuracy. | Using overly broad regex patterns. | Updating secure coding detection rules. | Refined SQL Injection detection logic and reduced false positives.
6 | Sprint 2 | 14-Jul-2026 | 23-Jul-2026 | Rajashekar Kanneboina | Improve vulnerability detection coverage. | Limiting detection to a few OWASP vulnerabilities. | Expanding Security Agent capabilities. | Added detection for XSS, CSRF, SSRF, XXE, JWT, Path Traversal, Command Injection, Weak Crypto, Weak Random and other vulnerabilities.
7 | Sprint 2 | 14-Jul-2026 | 23-Jul-2026 | Rajashekar Kanneboina | Standardize report generation modules. | Using inconsistent finding formats. | Testing report generation after every update. | Fixed report generation issues and standardized finding schema.
8 | Sprint 2 | 14-Jul-2026 | 23-Jul-2026 | Rajashekar Kanneboina | Improve Java language detection. | Depending only on file extensions. | Functional testing of detection modules. | Enhanced Java keyword detection for pasted source code.
9 | Sprint 2 | 14-Jul-2026 | 23-Jul-2026 | Rajashekar Kanneboina | Improve multi-agent orchestration. | Running agents sequentially without consolidation. | Maintaining modular architecture. | Integrated Code Analysis Agent and Security Agent into unified findings pipeline.
10 | Sprint 2 | 14-Jul-2026 | 23-Jul-2026 | Rajashekar Kanneboina | Perform complete integration testing. | Skipping final verification. | Maintaining project documentation and knowledge base. | Executed all Python and Java test cases and fixed identified issues.
11 | Sprint 3 | 24-Jul-2026 | 05-Aug-2026 | Rajashekar Kanneboina | Improve remediation quality using AI-generated secure fixes. | Providing only issue descriptions. | Enhancing remediation guidance. | Developed Remediation Agent with secure coding recommendations and corrected code examples.
12 | Sprint 3 | 24-Jul-2026 | 05-Aug-2026 | Rajashekar Kanneboina | Generate professional PR review summaries. | Writing manual review summaries. | Improving review readability. | Implemented PR Summary Agent with executive summary, severity breakdown and recommendations.
13 | Sprint 3 | 24-Jul-2026 | 05-Aug-2026 | Rajashekar Kanneboina | Improve developer dashboard visualization. | Displaying plain findings only. | Enhancing overall developer experience. | Added Code Health Score, severity cards, analytics dashboard and findings visualization.
14 | Sprint 3 | 24-Jul-2026 | 05-Aug-2026 | Rajashekar Kanneboina | Improve AI Assistant response quality. | Loading RAG pipeline during application startup. | Expanding secure coding knowledge base. | Implemented lazy loading for RAG components and optimized AI Assistant performance.
15 | Sprint 3 | 24-Jul-2026 | 05-Aug-2026 | Rajashekar Kanneboina | Improve conversation continuity. | Creating a new session for every query. | Enhancing developer interaction. | Added conversation history using Streamlit session state.
16 | Sprint 3 | 24-Jul-2026 | 05-Aug-2026 | Rajashekar Kanneboina | Improve report export quality. | Exporting incomplete reports. | Validating generated reports. | Enhanced PDF reports with findings, remediation suggestions and PR summary.
17 | Sprint 3 | 24-Jul-2026 | 05-Aug-2026 | Rajashekar Kanneboina | Optimize application startup performance. | Loading all AI components at launch. | Performance tuning and optimization. | Implemented lazy initialization for AI models and vector database.
18 | Sprint 3 | 24-Jul-2026 | 05-Aug-2026 | Rajashekar Kanneboina | Perform complete end-to-end validation. | Releasing without final verification. | Continuous testing and refinement. | Completed full multi-agent integration, validated Python and Java workflows, and finalized the project.